## Sheet1
Risk type | Risk | Probability | Impact | Management Strategy | Sorting Order
Project risk | Missed Deadline | 26.67% | 3.6667 | Plan ahead to identify possible harsh deadlines at least a week in advance. If the deadline cannot be moved, attempt to remove features from the deadline to make it manageable. | 0.97778
Technical risk | Too many packets for queue | 29.33% | 2.6667 | Disregard the benevolent packets or packets of specific protocalls and spin up new datacollectors to analyze the excluded packets. | 0.78222
Project risk | insufficient meetings | 31.67% | 2 | Prepare materials and questions for meetings to get the most out of them. | 0.63333
Technical risk | Improper IPC leading to bugs | 36% | 3 | Proactively test, and reactively look for libraries that are easier to use. | 1.08
Technical risk | Final platform has unforeseen incompatibilities | 10.33% | 3 | Utilize reputably cross-platform libraries. | 0.31
Project risk | User doesn’t understand interface | 23.33% | 1.3333 | Distribute user manuals and consider alternative interface designs. | 0.31111
Technical risk | interface is accessible by outside actors | 36.67% | 2.3333 | Only allow known clients to connect to the server. | 0.85556
Technical risk | Program crashes | 46.67% | 3 | Lots of Unit Testing to find issues before they become problems. | 1.4
Technical risk | Doesn't collect/show all packets | 23.33% | 3 | Research and implement the database with a high-performance option that can handle the task. | 0.7
Technical risk | Too slow to respond to packet data | 33.33% | 2.6667 | Display the packets before they receive analysis/a response. | 0.88889
Project risk | User confuses prod with testing | 6.667% | 1.6667 | Clearly demarcate the currently-running version. | 0.11111
Technical risk | Model misclassifies data | 71.67% | 2.3333 | Allow users to reclassify data for further retraining. | 1.6722
Project risk | Users trust model too much | 53.33% | 3.3333 | Inform the users on the confidence and pitfalls of using such a model. | 1.7778
Project risk | layout is confusing | 28.33% | 1.3333 | Distribute user manuals and consider alternative interface designs. | 0.37778
Project risk | layout does not meet user needs | 41.67% | 3.3333 | Assess and redesign interface according to requirements. | 1.3889
Project risk | Someone on the team gets sick/ becomes unable to work | 23.33% | 3.3333 | Maintain cohesion and communication so that work does not stall. | 0.77778
Technical risk | The code does not work | 16.33% | 4 | Lots of Unit Testing to find issues before they become problems. | 0.65333
Technical risk | Model fails to train | 16.67% | 3.3333 | Try different activation functions, learning rates, and model structures. | 0.55556
Business risk | Client drops project | 3.667% | 4.6667 | Speak with professor to identify new stakeholder to manage the project. | 0.17111
Project risk | Code has an unresolvable version conflict | 8.667% | 3.6667 | Identify equivalent libraries that can work together that can replace the confilicting libraries. | 0.31778
Business risk | Change to requirements | 43.33% | 2.6667 | Clarify requirements early on, and utilize a modular design which enables requirement changes. | 1.1556
Project risk | Internet Failure preventing work | 16.67% | 3 | Coordinate tasks so that work can be done when communication is impossible. | 0.5
Technical risk | Network packets in incompatible format | 32.67% | 2.6667 | Use a different library that is sufficient for our purposes and has readable data. | 0.87111
Project risk | Other classwork prevents work on the project | 63.33% | 2.6667 | Deprioritize other classwork and plan for it when unavoidable. | 1.6889
Project risk | Computer failure prevents work | 15.33% | 3.3333 | Backup data on cloud. Can use school PCs | 0.51111
Project risk | Computer stolen prevents work | 1.333% | 4.3333 | Backup data on cloud. Can use school PCs | 0.057778
Project risk | Local/National emergency of some kind prevents work | 4.033% | 4.3333 | In this case the project will be delayed until the end of the emergency. | 0.17478
Business risk | Change in management | 4.333% | 2 | Plan many meetings with new stakeholders to identify changes in the plan and stratagies to deal with those changes. | 0.086667
Project risk | Viability failure | 18.33% | 3 | Discuss the possibility of useful functions for the final pruduct with the stakeholders. | 0.55
Project risk | Project work stolen | 2.333% | 2 | Keep work computers safe and use passwords. | 0.046667
Project risk | Communication failure with client | 37.33% | 3.6667 | Plan a meeting to discuss the issues with communication. | 1.3689

## Sheet2
Risk type | Risk | Probability | Impact | Management Strategy | Sorting Order
Project risk | Users trust model too much | 53.33% | 3.3333 | Inform the users on the confidence and pitfalls of using such a model. | 1.7778
Project risk | Other classwork prevents work on the project | 63.33% | 2.6667 | Do a bad job on the other classwork. | 1.6889
Technical risk | Model misclassifies data | 71.67% | 2.3333 | Allow users to reclassify data for further retraining. | 1.6722
Technical risk | Program crashes | 46.67% | 3 | Lots of Unit Testing to find issues before they become problems. | 1.4
Project risk | layout does not meet user needs | 41.67% | 3.3333 | Assess and redesign interface according to requirements. | 1.3889
Project risk | Communication failure with client | 37.33% | 3.6667 | Plan a meeting to discuss the issues with communication. | 1.3689
Business risk | Change to requirements | 43.33% | 2.6667 | Clarify requirements early on, and utilize a modular design which enables requirement changes. | 1.1556
Technical risk | Improper IPC leading to bugs | 36% | 3 | Look for libraries that are easier to use. | 1.08
Project risk | Missed Deadline | 26.67% | 3.6667 | Plan ahead to identify possible harsh deadlines at least a week in advance. If the deadline cannot be moved, attempt to remove features from the deadline to make it manageable. | 0.97778
Technical risk | Too slow to respond to packet data | 33.33% | 2.6667 | Display the packets before they receive analysis/a response. | 0.88889
Technical risk | Network packets in incompatible format | 32.67% | 2.6667 | Use a different library that is sufficient for our purposes and has readable data. | 0.87111
Technical risk | interface is accessible by outside actors | 36.67% | 2.3333 | Only allow known clients to connect to the server. | 0.85556
Technical risk | Too many packets for queue | 29.33% | 2.6667 | Disregard the benevolent packets or packets of specific protocalls and spin up new datacollectors to analyze the excluded packets. | 0.78222
Project risk | Someone on the team gets sick/ becomes unable to work | 23.33% | 3.3333 | Maintain cohesion and communication so that work does not stall. | 0.77778
Technical risk | Doesn't collect/show all packets | 23.33% | 3 | Research and implement the database with a high-performance option that can handle the task. | 0.7
Technical risk | The code does not work | 16.33% | 4 | Lots of Unit Testing to find issues before they become problems. | 0.65333
Project risk | insufficient meetings | 31.67% | 2 | Prepare materials and questions for meetings to get the most out of them. | 0.63333
Technical risk | Model fails to train | 16.67% | 3.3333 | Try different activation functions, learning rates, and model structures. | 0.55556
Project risk | Viability failure | 18.33% | 3 | Discuss the possibility of useful functions for the final pruduct with the stakeholders. | 0.55
Project risk | Computer failure prevents work | 15.33% | 3.3333 | Backup data on cloud. Can use school PCs | 0.51111
Project risk | Internet Failure preventing work | 16.67% | 3 | Coordinate tasks so that work can be done when communication is impossible. | 0.5
Project risk | layout is confusing | 28.33% | 1.3333 | Distribute user manuals and consider alternative interface designs. | 0.37778
Project risk | Code has an unresolvable version conflict | 8.667% | 3.6667 | Identify equivalent libraries that can work together that can replace the confilicting libraries. | 0.31778
Project risk | User doesn’t understand interface | 23.33% | 1.3333 | Distribute user manuals and consider alternative interface designs. | 0.31111
Technical risk | Final platform has unforeseen incompatibilities | 10.33% | 3 | Utilize reputably cross-platform libraries. | 0.31
Project risk | Local/National emergency of some kind prevents work | 4.033% | 4.3333 | In this case the project will be delayed until the end of the emergency. | 0.17478
Business risk | Client drops project | 3.667% | 4.6667 | If occurs: Speak with professor to identify new stakeholder to manage the project. | 0.17111
Project risk | User confuses prod with testing | 6.667% | 1.6667 | Clearly demarcate the currently-running version. | 0.11111
Business risk | Change in management | 4.333% | 2 | Plan many meetings with new stakeholders to identify changes in the plan and stratagies to deal with those changes. | 0.086667
Project risk | Computer stolen prevents work | 1.333% | 4.3333 | Backup data on cloud. Can use school PCs | 0.057778
Project risk | Project work stolen | 2.333% | 2 | Keep work computers safe and use passwords. | 0.046667

## Joe
Risk type | Risk | Probability | Impact | Management Strategy
Project risk | Missed Deadline | 25% | 5
Technical risk | Too many packets for queue | 25% | 3
Project risk | insufficient meetings | 75% | 2
Technical risk | Improper IPC leading to bugs | 5% | 3
Technical risk | Final platform has unforeseen incompatibilities | 15% | 4
Project risk | User doesn’t understand interface | 10% | 2
Technical risk | interface is accessible by outside actors | 5% | 3
Technical risk | Program crashes | 15% | 4
Technical risk | Doesn't collect/show all packets | 10% | 3
Technical risk | Too slow to respond to packet data | 25% | 3
Project risk | User confuses prod with testing | 5% | 2
Technical risk | Model misclassifies data | 75% | 3
Project risk | Users trust model too much | 50% | 4
Project risk | layout is confusing | 25% | 2
Project risk | layout does not meet user needs | 50% | 3
Project risk | Someone on the team gets sick/ becomes unable to work | 25% | 3
Technical risk | The code does not work | 5% | 5
Technical risk | Model fails to train | 10% | 3
Business risk | Client drops project | 5% | 5
Project risk | Code has an unresolvable version conflict | 15% | 3
Business risk | Change to requirements | 50% | 2
Project risk | Internet Failure preventing work | 25% | 2
Technical risk | Network packets in incompatible format | 25% | 3
Project risk | Other classwork prevents work on the project | 25% | 3
Project risk | Computer failure prevents work | 3% | 4
Project risk | Computer stolen prevents work | 1% | 4
Project risk | Local/National emergency of some kind prevents work | 10% | 4
Business risk | Change in management | 5% | 2
Project risk | Viability failure | 10% | 3
Project risk | Project work stolen | 5% | 3
Project risk | Communication failure with client | 50% | 4

## Alex
Risk type | Risk | Probibility | Impact | Management Stratagy
Project risk | Missed Deadline | 25% | 4
Technical risk | Too many packets for queue | 38% | 2
Project risk | insufficent meetings | 10% | 2
Technical risk | Improper IPC leading to bugs | 78% | 3
Technical risk | Final platform has unforseen incompatabilities | 1% | 3
Project risk | User doesn’t understand interface | 40% | 1
Technical risk | interface is accesable by outside actors | 70% | 3
Technical risk | Program crashes | 100% | 1
Technical risk | Doesn't collect/show all packets | 35% | 2
Technical risk | Too slow to respond to packet data | 50% | 2
Project risk | User confuses prod with testing | 10% | 2
Technical risk | Model misclassifies data | 90% | 2
Project risk | Users trust model too much | 70% | 1
Project risk | layout is confusing | 40% | 1
Project risk | layout does not meet user needs | 60% | 3
Project risk | Someone on the team gets sick/ becomes unable to work | 12% | 4
Technical risk | The code does not work | 29% | 2
Technical risk | Model fails to train | 10% | 3
Business risk | Client drops project | 5% | 4
Project risk | Code has an unresolvable version conflict | 1% | 3
Business risk | Change to requirements | 50% | 2
Project risk | Internet Failure preventing work | 5% | 3
Technical risk | Network packets in incompatable format | 23% | 3
Project risk | Other classwork prevents work on the project | 65% | 2
Project risk | Computer failure prevents work | 10% | 4
Project risk | Computer stolen prevents work | 1% | 4
Project risk | Local/National emergency of some kind prevents work | 0.1% | 5
Business risk | Change in management | 3% | 2
Project risk | Viability failure | 40% | 2
Project risk | Project work stolen | 1% | 1
Project risk | Communication failure with client | 27% | 3

## Andrew
Risk type | Risk | Probibility | Impact | Management Stratagy
Project risk | Missed Deadline | 30% | 2 |  | 30% | 2
Technical risk | Too many packets for queue | 25% | 3 |  | 25% | 3
Project risk | insufficent meetings | 10% | 2 |  | 10% | 2
Technical risk | Improper IPC leading to bugs | 25% | 3 |  | 25% | 3
Technical risk | Final platform has unforseen incompatabilities | 15% | 2 |  | 15% | 2
Project risk | User doesn’t understand interface | 20% | 1 |  | 20% | 1
Technical risk | interface is accesable by outside actors | 35% | 1 |  | 35% | 1
Technical risk | Program crashes | 25% | 4 |  | 25% | 4
Technical risk | Doesn't collect/show all packets | 25% | 4 |  | 25% | 4
Technical risk | Too slow to respond to packet data | 25% | 3 |  | 25% | 3
Project risk | User confuses prod with testing | 5% | 1 |  | 5% | 1 | ??? Can we just remove this?
Technical risk | Model misclassifies data | 50% | 2 |  | 50% | 2 | ?
Project risk | Users trust model too much | 40% | 5 |  | 40% | 5 | What do you mean, I moved your to your slide
Project risk | layout is confusing | 20% | 1 |  | 20% | 1
Project risk | layout does not meet user needs | 15% | 4 |  | 15% | 4 | I put them in the main table
Project risk | Someone on the team gets sick/ becomes unable to work | 33% | 3 |  | 33% | 3
Technical risk | The code does not work | 15% | 5 |  | 15% | 5
Technical risk | Model fails to train | 30% | 4 |  | 30% | 4
Business risk | Client drops project | 1% | 5 |  | 1% | 5
Project risk | Code has an unresolvable version conflict | 10% | 5 |  | 10% | 5
Business risk | Change to requirements | 30% | 4 |  | 30% | 4
Project risk | Internet Failure preventing work | 20% | 4 |  | 20% | 4
Technical risk | Network packets in incompatable format | 50% | 2 |  | 50% | 2
Project risk | Other classwork prevents work on the project | 100% | 3 |  | 100% | 3
Project risk | Computer failure prevents work | 33% | 2 |  | 33% | 2
Project risk | Computer stolen prevents work | 2% | 5 |  | 2% | 5
Project risk | Local/National emergency of some kind prevents work | 2% | 4 |  | 2% | 4
Business risk | Change in management | 5% | 2 |  | 5% | 2
Project risk | Viability failure | 5% | 4 |  | 5% | 4
Project risk | Project work stolen | 1% | 2 |  | 1% | 2
Project risk | Communication failure with client | 35% | 4 |  | 35% | 4